## Sheet1
Great Art Project Schedule
Timeline
Task | Sub-Task |  | Estimated Hours |  | Actual Hours
Specifications Document
Interview Client |  |  | 3 |  | 2.5
Planning |  |  | 1.5 |  | 1
Research | Legal |  | 2 |  | 1.5
| SEO |  | 1 |  | 0.75
| Hosting |  | 1 |  | 0.5
| Domain Name |  | 1 |  | 0.5
Design | Sitemap |  | 1 |  | 0.5
| Wireframes |  | 2 |  | 3.5
|  | Total Hours | 12.5 | Total Hours | 10.75
Website Construction | Design |  | 10 |  | 13
| Research |  | 10 |  | 14
| Multimedia work |  | 20 |  | 21
|  | Total Hours | 40 | Total Hours | 48
Budget
Task |  | Estimated Hours |  | Actual Hours |  | Rate ($ per hour)
Specifications Document |  | 12.5 |  | 10.75 |  | 27
Website Implementation |  | 40 |  | 48
| Total Est. Hours | 52.5 | Total Actual Hours | 58.75 | Sub-Total | 1586.25
Expenses |  | Option 1 | Option 2
Domain Name | (per year) | 19.99 | 19.99
Hosting | (per month) | 6.99 | 6.99
Hosting (each month after 1st month) |  | 10.99 | 10.99
| Total (1 year) | 147.87 | 147.87
| Rate | 1586.25
| Expenses | 147.87
| Total Cost | 1734.12